## Build in Five Project Plan
ID | Task Mode | WBS | Task Name | Status | Duration | Start | Finish | Predecessors | Resource Names | Deliverable Ref | Notes / Source
1 | Auto Scheduled | 1 | PHASE 0: FOUNDATION | In Progress | 20 days | Mon 03/02/26 | Fri 03/27/26 |  |  |  | Weeks 1-4. Setting up all building blocks for live demos.
2 | Manually Scheduled | 1.1 | Programme Setup & Governance | In Progress | 10 days | Mon 03/02/26 | Fri 03/13/26 |  | Azmain Hossain |  | Establish project governance, comms, and folder structure.
3 | Manually Scheduled | 1.1.1 | Create B5 SharePoint folder structure (separate from Clara) | Complete | 1 day | Mon 03/02/26 | Mon 03/02/26 |  | Azmain Hossain |  | Dedicated B5 folder, not under Clara/Genie.
4 | Manually Scheduled | 1.1.2 | Consolidate all B5 documents into SharePoint | In Progress | 3 days | Mon 03/02/26 | Wed 03/04/26 |  | Azmain Hossain |  | Martin scoping doc, expanded scope, GSD framework, POC files.
5 | Manually Scheduled | 1.1.3 | Establish standup cadence (Martin, Azmain, Richard, Ben VH) | In Progress | 2 days | Mon 03/02/26 | Tue 03/03/26 |  | Azmain Hossain | D18 | Recurring calendar invites. Agreed 27-Feb meeting.
6 | Manually Scheduled | 1.1.4 | Define RACI matrix and circulate for sign-off | Complete | 2 days | Tue 03/03/26 | Wed 03/04/26 |  | Azmain Hossain | D17 | See v4.0 Section 17.
7 | Manually Scheduled | 1.1.5 | Finalise phase gate entry/exit criteria | Complete | 1 day | Wed 03/04/26 | Wed 03/04/26 |  | Azmain Hossain | D13 | Documented in v4.0 Section 16.
8 | Manually Scheduled | 1.1.6 | Confirm fortnightly review cadence and escalation path | Complete | 1 day | Wed 03/04/26 | Wed 03/04/26 |  | Azmain Hossain | D18
9 | Manually Scheduled | 1.1.7 | Submit dedicated team proposal for leadership approval | Complete | 2 days | Wed 03/04/26 | Thu 03/05/26 |  | Richard Dosoo | D30 | Submitted to Diya Sawhny. Recommend start lean.
10 | Manually Scheduled | 1.1.8 | Obtain Stacy sign-off for Martin to deprioritise Cat Accelerate/Canopus | Planned | 5 days | Tue 03/03/26 | Sat 03/07/26 |  | Richard Dosoo |  | Critical dependency for Martin 75% allocation.
11 | Manually Scheduled | 1.1.9 | Martin full review of v4.0 plan and expanded scope | In Progress | 5 days | Mon 03/02/26 | Fri 03/06/26 |  | Martin Davies |  | First week back from holiday. Coming up to speed.
12 | Manually Scheduled | 1.1.10 | Create naming and positioning one-pager | Complete | 2 days | Mon 03/02/26 | Tue 03/03/26 |  | Richard Dosoo | D1 | "Build in Five" external, "Cursor in Pipeline" internal.
13 | Manually Scheduled | 1.2 | Licensing & Access | In Progress | 10 days | Mon 03/02/26 | Fri 03/13/26 |  | Richard Dosoo |  | Confirm all tooling access for team and pilot SEs.
14 | Manually Scheduled | 1.2.1 | Confirm Cursor licence availability for SEs and Advisory | Complete | 3 days | Mon 03/02/26 | Wed 03/04/26 |  | IT / Procurement | D2 | Procurement dependency.
15 | Manually Scheduled | 1.2.2 | Confirm Amazon Bedrock access for Claude Code (via Dennis Climent) | In Progress | 5 days | Mon 03/02/26 | Fri 03/06/26 |  | Azmain Hossain | D2 | Corporate-approved Anthropic access path.
16 | Manually Scheduled | 1.2.3 | Set up Bedrock OIDC federation / IAM roles | Planned | 5 days | Thu 03/05/26 | Wed 03/11/26 | 14 | Azmain Hossain |  | Shared dependency with AI Enablement Platform.
17 | Manually Scheduled | 1.2.4 | Confirm GitHub org permits new repo creation per factory app | Planned | 3 days | Mon 03/02/26 | Wed 03/04/26 |  | Ben Van Houten
18 | Manually Scheduled | 1.2.5 | Verify Terraform state management (S3 backend) accessible | Planned | 2 days | Tue 03/03/26 | Wed 03/04/26 |  | Ben Van Houten
19 | Manually Scheduled | 1.2.6 | Submit Entra ID app registration requests for new factory apps | Planned | 2 days | Mon 03/02/26 | Tue 03/03/26 |  | IT / Security |  | LONGEST LEAD TIME. Submit Week 1.
20 | Manually Scheduled | 1.3 | Application Factory Infrastructure Validation | In Progress | 15 days | Mon 03/02/26 | Fri 03/20/26 |  | Richard Dosoo |  | Validate live infra is ready for B5 workloads.
21 | Manually Scheduled | 1.3.1 | Confirm ECS Fargate cluster capacity for 10-15 additional services | Planned | 3 days | Mon 03/02/26 | Wed 03/04/26 |  | Ben Van Houten |  | Check with Platform/DevOps.
22 | Manually Scheduled | 1.3.2 | Validate Terraform modules for new app provisioning | Complete | 5 days | Tue 03/03/26 | Sat 03/07/26 |  | Richard Dosoo | D19 | Live and proven with IRP Adoption Tracker.
23 | Manually Scheduled | 1.3.3 | Test end-to-end deployment pipeline: GitHub → ECR → ECS (dev) | Planned | 3 days | Fri 03/06/26 | Tue 03/10/26 | 22 | Ben Van Houten |  | Deploy a test app through full pipeline.
24 | Manually Scheduled | 1.3.4 | Validate branch-driven deploy: develop→dev, staging→staging, main→prod | Planned | 2 days | Tue 03/10/26 | Wed 03/11/26 | 23 | Ben Van Houten
25 | Manually Scheduled | 1.3.5 | Confirm ALB path-based routing and target group creation for new apps | Planned | 2 days | Tue 03/10/26 | Wed 03/11/26 | 23 | Ben Van Houten
26 | Manually Scheduled | 1.3.6 | Validate Route 53 subdomain creation (*.advisory-appfactory.com) | Planned | 1 day | Wed 03/11/26 | Wed 03/11/26 | 25 | Ben Van Houten |  | dev.advisory-appfactory.com confirmed live.
27 | Manually Scheduled | 1.3.7 | Confirm Secrets Manager pattern (/factory/{app}/{env}/*) | Planned | 1 day | Wed 03/11/26 | Wed 03/11/26 | 25 | Ben Van Houten
28 | Manually Scheduled | 1.3.8 | Test Entra ID SSO/OIDC authentication for a new factory app | Planned | 3 days | Thu 03/12/26 | Mon 03/16/26 | 18,26 | Ben Van Houten |  | Depends on Entra ID registration.
29 | Manually Scheduled | 1.3.9 | Validate PR guardrails (migration validation, pytest, tsc+vite build) | Planned | 2 days | Thu 03/12/26 | Fri 03/13/26 | 24 | Ben Van Houten
30 | Manually Scheduled | 1.3.10 | Test AI agent label-driven GitHub Actions workflows | Planned | 2 days | Fri 03/13/26 | Mon 03/16/26 | 29 | Richard Dosoo |  | user-feedback, ai-execute, ai-approve labels.
31 | Manually Scheduled | 1.3.11 | Create Application Factory operations runbook | Complete | 3 days | Sat 03/07/26 | Wed 03/11/26 |  | Richard Dosoo | D20
32 | Manually Scheduled | 1.3.12 | Define factory cost and lifecycle management policy | Planned | 3 days | Sat 03/14/26 | Wed 03/18/26 |  | Richard Dosoo | D22 | Scale-to-zero, 30-day inactivity flag, £750/mo cap.
33 | Manually Scheduled | 1.3.13 | Configure AWS budget alerting at 80% (£600) threshold | Planned | 1 day | Wed 03/18/26 | Wed 03/18/26 | 32 | Ben Van Houten
34 | Manually Scheduled | 1.3.14 | Create Application Factory architecture deck (7 slides) | Complete | 3 days | Mon 03/02/26 | Wed 03/04/26 |  | Richard Dosoo | D23 | Already completed.
35 | Manually Scheduled | 1.4 | .cursorrules v2 & Development Guardrails | Complete | 10 days | Mon 03/02/26 | Fri 03/13/26 |  | Richard Dosoo |  | Enforce mandatory tech stack automatically.
36 | Manually Scheduled | 1.4.1 | Finalise .cursorrules v2 full architectural specification | Complete | 3 days | Mon 03/02/26 | Wed 03/04/26 |  | Richard Dosoo | D24 | Tech stack + security + conventions enforcement.
37 | Manually Scheduled | 1.4.2 | Add tech stack enforcement (FastAPI, React 18, Vite, Tailwind, SQLAlchemy, PG15) | Complete | 2 days | Mon 03/02/26 | Tue 03/03/26 |  | Richard Dosoo
38 | Manually Scheduled | 1.4.3 | Add Application Factory conventions (UUIDs, soft deletes, audit cols, brand colours) | Complete | 1 day | Tue 03/03/26 | Tue 03/03/26 |  | Richard Dosoo |  | #1a2942 navy, #00a4a6 teal, #f0f4f8 light grey.
39 | Manually Scheduled | 1.4.4 | Add project structure enforcement (backend/app/{api,models,schemas,core}) | Complete | 1 day | Tue 03/03/26 | Tue 03/03/26 |  | Richard Dosoo
40 | Manually Scheduled | 1.4.5 | Add Docker patterns (multi-stage builds, AUTH_MODE=local bypass) | Complete | 1 day | Wed 03/04/26 | Wed 03/04/26 |  | Richard Dosoo
41 | Manually Scheduled | 1.4.6 | Add CI/CD rules (OIDC federation, PR guardrails, branch deploys) | Complete | 1 day | Wed 03/04/26 | Wed 03/04/26 |  | Richard Dosoo
42 | Manually Scheduled | 1.4.7 | Add security rules (no hardcoded secrets, no eval, input validation, CORS) | Complete | 1 day | Wed 03/04/26 | Wed 03/04/26 |  | Richard Dosoo
43 | Manually Scheduled | 1.4.8 | Add pause-and-ask rules (new deps, auth changes, DB schema changes) | Complete | 1 day | Thu 03/05/26 | Thu 03/05/26 |  | Richard Dosoo
44 | Manually Scheduled | 1.4.9 | Test .cursorrules with sample project in Cursor IDE | Planned | 3 days | Fri 03/06/26 | Tue 03/10/26 | 36 | Martin Davies |  | Martin validates rules produce correct scaffolding.
45 | Manually Scheduled | 1.4.10 | Create CLAUDE.md policy file aligned with .cursorrules | Planned | 3 days | Fri 03/06/26 | Tue 03/10/26 | 36 | Azmain Hossain |  | For Claude Code / AI Enablement Platform alignment.
46 | Manually Scheduled | 1.5 | Build in Five Studio Productisation | In Progress | 15 days | Tue 03/03/26 | Sat 03/21/26 |  | Richard Dosoo |  | Both Claude Project and web app versions.
47 | Manually Scheduled | 1.5.1 | Finalise B5 Studio Claude Project instructions | Complete | 3 days | Tue 03/03/26 | Thu 03/05/26 |  | Richard Dosoo | D25 | For use in claude.ai.
48 | Manually Scheduled | 1.5.2 | Define 4-step guided workflow prompts | Complete | 2 days | Tue 03/03/26 | Wed 03/04/26 |  | Azmain Hossain |  | Problem Definition → Solution Thinking → Recommendation → Spec Generation.
49 | Manually Scheduled | 1.5.3 | Finalise ~9 diagnostic questions (adapted from GSD framework) | Complete | 2 days | Wed 03/04/26 | Thu 03/05/26 |  | Azmain Hossain |  | Problem-first framing for non-technical users.
50 | Manually Scheduled | 1.5.4 | Implement complexity guard (5 levels: skill-only to full web app) | Planned | 3 days | Fri 03/06/26 | Tue 03/10/26 | 49 | Richard Dosoo |  | Auto-evaluates whether full app needed or simpler solution.
51 | Manually Scheduled | 1.5.5 | Define App Brief JSON schema (roles, entities, pages, workflows, integrations) | Planned | 3 days | Fri 03/06/26 | Tue 03/10/26 | 49 | Martin Davies
52 | Manually Scheduled | 1.5.6 | Define Scaffold Prompt template (enforces mandatory tech stack) | Planned | 3 days | Tue 03/10/26 | Thu 03/12/26 | 51 | Martin Davies |  | Self-contained prompt → paste into Cursor → working app.
53 | Manually Scheduled | 1.5.7 | Fix bugs in B5 Studio web app (Docker-based POC) | Planned | 5 days | Tue 03/10/26 | Sat 03/14/26 |  | Richard Dosoo |  | Richard built POC, noted as "a bit buggy".
54 | Manually Scheduled | 1.5.8 | Test Studio end-to-end: problem input → App Brief → Scaffold Prompt output | Planned | 3 days | Sat 03/14/26 | Wed 03/18/26 | 52,53 | Martin Davies
55 | Manually Scheduled | 1.5.9 | Define pre-built answers for sales demo fast-track mode | Planned | 3 days | Sat 03/14/26 | Wed 03/18/26 | 52 | Martin Davies |  | Skip diagnostic steps for live pre-sales demos.
56 | Manually Scheduled | 1.5.10 | Deploy B5 Studio web app to Application Factory (dev env) | Planned | 3 days | Wed 03/18/26 | Fri 03/20/26 | 54,23 | Ben Van Houten
57 | Manually Scheduled | 1.6 | Sandbox Environment & Demo Data Preparation | Planned | 15 days | Tue 03/03/26 | Sat 03/21/26 |  | Martin Davies |  | HIGHEST-RISK OPEN DEPENDENCY. Needs named owner.
58 | Manually Scheduled | 1.6.1 | Identify and confirm sandbox dataset owner | Planned | 3 days | Tue 03/03/26 | Thu 03/05/26 |  | Richard Dosoo | D3 | Highest-risk dependency per v4.0 Next Steps.
59 | Manually Scheduled | 1.6.2 | Define sandbox dataset specification (data types, volumes, schemas) | Planned | 5 days | Thu 03/05/26 | Wed 03/11/26 | 58 | Martin Davies | D3
60 | Manually Scheduled | 1.6.3 | Prepare sample customer CSV for Scenario 1 (Data Ingestion) | Planned | 3 days | Wed 03/11/26 | Fri 03/13/26 | 59 | Martin Davies |  | Bordereaux-style data, London market MGA use case.
61 | Manually Scheduled | 1.6.4 | Prepare ExposureIQ sample query configurations for Scenario 2 | Planned | 3 days | Wed 03/11/26 | Fri 03/13/26 | 59 | Martin Davies |  | Exposure by geography, peril, line of business.
62 | Manually Scheduled | 1.6.5 | Prepare sample event payloads for Scenario 3 (Webhook/Guidewire) | Planned | 3 days | Wed 03/11/26 | Fri 03/13/26 | 59 | Martin Davies |  | Underwriting decision events from UnderwriteIQ.
63 | Manually Scheduled | 1.6.6 | Validate sandbox environment accessibility and data quality | Planned | 3 days | Sat 03/14/26 | Wed 03/18/26 | 60,61,62 | Martin Davies |  | Must be validated before Phase 1 gate.
64 | Manually Scheduled | 1.6.7 | Establish quarterly sandbox refresh process | Planned | 2 days | Wed 03/18/26 | Thu 03/19/26 | 63 | Martin Davies
65 | Manually Scheduled | 1.7 | Demo Scenario Scaffold Prompts | Planned | 15 days | Mon 03/09/26 | Fri 03/27/26 |  | Martin Davies |  | Three scenarios proving "open platform" story.
66 | Manually Scheduled | 1.7.1 | Consult Rahul on demo scenario validation (exceedance relevance) | Planned | 3 days | Mon 03/09/26 | Wed 03/11/26 |  | Martin Davies |  | Two of three scenarios are UW IQ — should Responder be used?
67 | Manually Scheduled | 1.7.2 | Scenario 1: Data Ingestion Pipeline — Scaffold Prompt Development | Planned | 5 days | Wed 03/11/26 | Tue 03/17/26 | 66 | Martin Davies | D6 | "Your platform can't handle our data formats."
68 | Manually Scheduled | 1.7.2.1 | Define FastAPI backend with file upload endpoint | Planned | 2 days | Wed 03/11/26 | Thu 03/12/26 |  | Martin Davies
69 | Manually Scheduled | 1.7.2.2 | Implement schema validation logic against Risk Data Lake schema | Planned | 2 days | Thu 03/12/26 | Fri 03/13/26 | 68 | Martin Davies
70 | Manually Scheduled | 1.7.2.3 | Implement CSV transform to MRI format and sandbox write | Planned | 2 days | Fri 03/13/26 | Mon 03/16/26 | 69 | Martin Davies
71 | Manually Scheduled | 1.7.2.4 | Include sample data in scaffold prompt | Planned | 1 day | Mon 03/16/26 | Mon 03/16/26 | 70 | Martin Davies
72 | Manually Scheduled | 1.7.2.5 | Create pre-built fallback branch for live demo failure | Planned | 1 day | Tue 03/17/26 | Tue 03/17/26 | 71 | Martin Davies
73 | Manually Scheduled | 1.7.3 | Scenario 2: Custom Analytics Interface — Scaffold Prompt Development | Planned | 5 days | Wed 03/11/26 | Tue 03/17/26 | 66 | Martin Davies | D6 | "We need custom analytics views."
74 | Manually Scheduled | 1.7.3.1 | Define React scaffold with Tailwind and ExposureIQ API wrapper | Planned | 2 days | Wed 03/11/26 | Thu 03/12/26 |  | Martin Davies
75 | Manually Scheduled | 1.7.3.2 | Implement custom aggregation views (geography, peril, LOB) | Planned | 2 days | Thu 03/12/26 | Fri 03/13/26 | 74 | Martin Davies
76 | Manually Scheduled | 1.7.3.3 | Include sample query configurations | Planned | 1 day | Mon 03/16/26 | Mon 03/16/26 | 75 | Martin Davies
77 | Manually Scheduled | 1.7.3.4 | Create pre-built fallback branch | Planned | 1 day | Tue 03/17/26 | Tue 03/17/26 | 76 | Martin Davies
78 | Manually Scheduled | 1.7.4 | Scenario 3: Guidewire Integration (Webhook) — Scaffold Prompt Development | Planned | 5 days | Fri 03/13/26 | Thu 03/19/26 | 66 | Martin Davies | D6 | "How does this integrate with Guidewire?" Golden Bear use case.
79 | Manually Scheduled | 1.7.4.1 | Define event listener and webhook endpoint | Planned | 2 days | Fri 03/13/26 | Mon 03/16/26 |  | Martin Davies
80 | Manually Scheduled | 1.7.4.2 | Implement notification dispatcher and sample payloads | Planned | 2 days | Mon 03/16/26 | Tue 03/17/26 | 79 | Martin Davies
81 | Manually Scheduled | 1.7.4.3 | Create pre-built fallback branch | Planned | 1 day | Wed 03/18/26 | Wed 03/18/26 | 80 | Martin Davies
82 | Manually Scheduled | 1.7.5 | End-to-end testing of all three scaffold prompts in Cursor | Planned | 3 days | Thu 03/19/26 | Mon 03/23/26 | 72,77,81 | Martin Davies |  | Full test within 30 mins before any demo.
83 | Manually Scheduled | 1.7.6 | Test deployment of each scenario to App Factory (dev) | Planned | 3 days | Mon 03/23/26 | Wed 03/25/26 | 82 | Ben Van Houten |  | ~10 minutes per deployment target.
84 | Manually Scheduled | 1.7.7 | Build combined narrative script (IN → ON TOP → OUT) | Planned | 2 days | Wed 03/25/26 | Thu 03/26/26 | 83 | Martin Davies |  | Systematically dismantles "black box" objection.
85 | Manually Scheduled | 1.8 | Exceedance Event Preparation (~21 March) | Planned | 15 days | Thu 03/05/26 | Sat 03/21/26 |  | Richard Dosoo |  | Ben Brooks has innovation panel slot. Content approval required.
86 | Manually Scheduled | 1.8.1 | Determine exceedance content approval process and timeline | Planned | 3 days | Thu 03/05/26 | Sat 03/07/26 |  | Richard Dosoo |  | Exceedance has its own approval process.
87 | Manually Scheduled | 1.8.2 | Decide which demo scenario(s) to present at exceedance | Planned | 2 days | Sat 03/07/26 | Tue 03/10/26 | 86 | Martin Davies |  | Depends on Rahul consultation re: UW IQ vs Responder.
88 | Manually Scheduled | 1.8.3 | Prepare exceedance demo script and talking points | Planned | 3 days | Tue 03/10/26 | Thu 03/12/26 | 87 | Richard Dosoo
89 | Manually Scheduled | 1.8.4 | Create exceedance presentation materials | Planned | 3 days | Thu 03/12/26 | Mon 03/16/26 | 88 | Richard Dosoo
90 | Manually Scheduled | 1.8.5 | Rehearsal run-through of live demo for exceedance | Planned | 2 days | Mon 03/16/26 | Tue 03/17/26 | 89 | Martin Davies |  | Full rehearsal including failure fallback.
91 | Manually Scheduled | 1.8.6 | Submit content for exceedance approval | Planned | 2 days | Tue 03/17/26 | Wed 03/18/26 | 90 | Richard Dosoo
92 | Manually Scheduled | 1.8.7 | Exceedance event delivery | Planned | 1 day | Sat 03/21/26 | Sat 03/21/26 | 91 | Richard Dosoo, Martin Davies |  | TARGET DATE. Innovation panel.
93 | Manually Scheduled | 1.9 | CRM Tagging & Measurement Baseline | Planned | 10 days | Mon 03/09/26 | Fri 03/20/26 |  | Azmain Hossain |  | Establish baseline before Phase 1 demos.
94 | Manually Scheduled | 1.9.1 | Define CRM deal-tagging spec ("Build in Five" + "App Factory deployed") | Planned | 3 days | Mon 03/09/26 | Wed 03/11/26 |  | Azmain Hossain | D5
95 | Manually Scheduled | 1.9.2 | Implement deal tags in CRM system | Planned | 3 days | Wed 03/11/26 | Fri 03/13/26 | 94 |  | D12
96 | Manually Scheduled | 1.9.3 | Define measurement and reporting specification | Planned | 3 days | Wed 03/11/26 | Fri 03/13/26 |  | Azmain Hossain | D11 | Win rate, demo velocity, prototype-to-deploy, cycle compression.
97 | Manually Scheduled | 1.9.4 | Establish current baseline: win rates and demo prep times | Planned | 10 days | Mon 03/09/26 | Fri 03/20/26 |  |  | D10 | Must be completed before Phase 1. Rolling data collection.
98 | Manually Scheduled | 1.9.5 | Configure monthly factory health reporting template | Planned | 2 days | Fri 03/13/26 | Mon 03/16/26 | 96 | Azmain Hossain |  | Active apps, cost, deploy success rate, decommissions.
99 | Manually Scheduled | 1.10 | IRP MCP Server Integration Planning | Planned | 10 days | Thu 03/05/26 | Wed 03/18/26 |  | Azmain Hossain |  | Formally map dependency on Cihan/Bala MCP server.
100 | Manually Scheduled | 1.10.1 | Map B5 demo dependencies on IRP Navigator MCP server capabilities | Planned | 3 days | Thu 03/05/26 | Sat 03/07/26 |  | Azmain Hossain |  | suggest_workflow, execute_API, graph_explore, etc.
101 | Manually Scheduled | 1.10.2 | Schedule alignment meeting with Cihan/Bala (IRP Navigator team) | Planned | 1 day | Sat 03/07/26 | Sat 03/07/26 | 100 | Azmain Hossain
102 | Manually Scheduled | 1.10.3 | Test MCP server access from B5 demo environment | Planned | 3 days | Tue 03/10/26 | Thu 03/12/26 | 101 | Martin Davies |  | 18 Postman collections, developer portal docs.
103 | Manually Scheduled | 1.10.4 | Document MCP server integration points for scaffold prompts | Planned | 2 days | Thu 03/12/26 | Fri 03/13/26 | 102 | Martin Davies
104 | Manually Scheduled | 1.11 | Phase 0 Gate Review | Planned | 1 day | Fri 03/27/26 | Fri 03/27/26 |  | Azmain Hossain | D14 | Confirm all Phase 1 entry criteria met.
105 | Manually Scheduled | 1.11.1 | Complete Phase 1 rollout checklist | Planned | 2 days | Wed 03/25/26 | Thu 03/26/26 |  | Azmain Hossain | D14
106 | Manually Scheduled | 1.11.2 | Verify: D2-D5 signed off, D6 tested, D19 live on dev, D24+D25 deployed | Planned | 1 day | Thu 03/26/26 | Thu 03/26/26 | 105 | Azmain Hossain
107 | Manually Scheduled | 1.11.3 | Confirm pilot SEs selected (max 2) | Planned | 3 days | Fri 03/20/26 | Tue 03/24/26 |  | Richard Dosoo |  | Pre-Sales leadership allocates pilot SEs.
108 | Manually Scheduled | 1.11.4 | Confirm AS capacity for Phase 1 (8-10 hrs/wk) | Planned | 1 day | Thu 03/26/26 | Thu 03/26/26 |  | Azmain Hossain
109 | Manually Scheduled | 1.11.5 | Phase 0 → Phase 1 gate decision | Planned | 1 day | Fri 03/27/26 | Fri 03/27/26 | 106,107,108 | Richard Dosoo |  | Go/No-Go for live demos.
110 | Auto Scheduled | 2 | PHASE 1: LIVE DEMOS & PILOT | Planned | 20 days | Mon 03/30/26 | Fri 04/24/26 |  |  |  | Weeks 5-8. First live client demos and App Factory deployments.
111 | Manually Scheduled | 2.1 | Live Demo Execution (3-4 per week) | Planned | 20 days | Mon 03/30/26 | Fri 04/24/26 |  | Martin Davies |  | AS leads/co-leads every demo with pilot SEs.
112 | Manually Scheduled | 2.1.1 | Prepare Advisory Services runbook for demo execution | Planned | 3 days | Mon 03/30/26 | Wed 04/01/26 |  | Martin Davies | D8
113 | Manually Scheduled | 2.1.2 | Create pre-demo checklist (mandatory for every demo) | Planned | 2 days | Mon 03/30/26 | Tue 03/31/26 |  | Martin Davies |  | Scaffold tested, fallback branch confirmed, sandbox valid, network backup.
114 | Manually Scheduled | 2.1.3 | Week 5: First live demos (AS-led, SE shadowing) | Planned | 5 days | Mon 03/30/26 | Fri 04/03/26 |  | Martin Davies, Richard Dosoo |  | 3-4 demos target. First exposure to real prospects.
115 | Manually Scheduled | 2.1.4 | Week 5 demo retrospective and template refinement | Planned | 1 day | Fri 04/03/26 | Fri 04/03/26 | 114 | Azmain Hossain
116 | Manually Scheduled | 2.1.5 | Week 6: Live demos (AS-led, SE co-piloting) | Planned | 5 days | Mon 04/06/26 | Fri 04/10/26 | 115 | Martin Davies
117 | Manually Scheduled | 2.1.6 | Week 6 demo retrospective | Planned | 1 day | Fri 04/10/26 | Fri 04/10/26 | 116 | Azmain Hossain
118 | Manually Scheduled | 2.1.7 | Week 7: Live demos (SE co-leading with AS support) | Planned | 5 days | Mon 04/13/26 | Fri 04/17/26 | 117 | Martin Davies
119 | Manually Scheduled | 2.1.8 | Week 7 demo retrospective | Planned | 1 day | Fri 04/17/26 | Fri 04/17/26 | 118 | Azmain Hossain
120 | Manually Scheduled | 2.1.9 | Week 8: Live demos (SE leading, AS on standby) | Planned | 5 days | Mon 04/20/26 | Fri 04/24/26 | 119 | Martin Davies |  | Transition toward SE independence.
121 | Manually Scheduled | 2.1.10 | Week 8 demo retrospective and Phase 1 review | Planned | 1 day | Fri 04/24/26 | Fri 04/24/26 | 120 | Azmain Hossain
122 | Manually Scheduled | 2.1.11 | Capture and log SE feedback after each demo | Planned | 20 days | Mon 03/30/26 | Fri 04/24/26 |  | Azmain Hossain |  | Ongoing throughout Phase 1.
123 | Manually Scheduled | 2.2 | Application Factory Deployments | Planned | 20 days | Mon 03/30/26 | Fri 04/24/26 |  | Ben Van Houten |  | Deploy demo prototypes post-demo. Target: 6+ in phase.
124 | Manually Scheduled | 2.2.1 | Deploy first demo prototype to App Factory (within 48 hrs of demo) | Planned | 2 days | Wed 04/01/26 | Thu 04/02/26 |  | Ben Van Houten |  | Prospect gets live URL to continue exploring.
125 | Manually Scheduled | 2.2.2 | Establish deployment SOP for post-demo prototype handoff | Planned | 3 days | Mon 03/30/26 | Wed 04/01/26 |  | Ben Van Houten
126 | Manually Scheduled | 2.2.3 | Track prototype-to-deployment rate (target ≥60% in Phase 1) | Planned | 20 days | Mon 03/30/26 | Fri 04/24/26 |  | Azmain Hossain
127 | Manually Scheduled | 2.2.4 | Validate factory-manifest.json for each deployed app | Planned | 20 days | Mon 03/30/26 | Fri 04/24/26 |  | Ben Van Houten |  | CPU, memory, health checks, env vars.
128 | Manually Scheduled | 2.2.5 | First factory cost review (within budget cap) | Planned | 1 day | Fri 04/17/26 | Fri 04/17/26 |  | Azmain Hossain |  | £750/mo cap.
129 | Manually Scheduled | 2.3 | Sales Team Engagement & Local vs Deployed Decision | Planned | 10 days | Mon 03/30/26 | Fri 04/10/26 |  | Richard Dosoo
130 | Manually Scheduled | 2.3.1 | Meet with sales team to determine localhost vs deployed preference | Planned | 3 days | Mon 03/30/26 | Wed 04/01/26 |  | Richard Dosoo |  | Richard meeting sales team, mentioned 27-Feb.
131 | Manually Scheduled | 2.3.2 | Agree demo delivery model based on sales feedback | Planned | 2 days | Wed 04/01/26 | Thu 04/02/26 | 130 | Richard Dosoo
132 | Manually Scheduled | 2.3.3 | Begin CRM deal tagging for B5 demos | Planned | 1 day | Mon 03/30/26 | Mon 03/30/26
133 | Manually Scheduled | 2.4 | AI Enablement Platform Pilot (Parallel Track) | Planned | 20 days | Mon 03/30/26 | Fri 04/24/26 |  | Azmain Hossain |  | Separate programme, sync points with B5.
134 | Manually Scheduled | 2.4.1 | Deploy MCP Tier 1 servers (SharePoint, Snowflake R/O, Atlassian, Filesystem) | Planned | 10 days | Mon 03/30/26 | Fri 04/10/26 |  | Azmain Hossain |  | Enables live data in B5 demos from Week 5.
135 | Manually Scheduled | 2.4.2 | Recruit 10-20 pilot users for AI Platform | Planned | 5 days | Mon 03/30/26 | Fri 04/03/26 |  | Azmain Hossain
136 | Manually Scheduled | 2.4.3 | Onboard pilot users with starter templates | Planned | 10 days | Fri 04/03/26 | Thu 04/16/26 | 135 | Azmain Hossain |  | Weekly feedback collection.
137 | Manually Scheduled | 2.4.4 | Build 4 priority skills: excel-combiner, dashboard, snowflake-query, moody-branded-doc | Planned | 15 days | Mon 03/30/26 | Fri 04/17/26 |  | Azmain Hossain
138 | Manually Scheduled | 2.4.5 | Validate MCP Tier 1 available for B5 demo live data | Planned | 2 days | Fri 04/10/26 | Mon 04/13/26 | 134 | Azmain Hossain |  | SYNC POINT: B5 demos use live Snowflake/SharePoint data.
139 | Manually Scheduled | 2.5 | Phase 1 Gate Review | Planned | 1 day | Fri 04/24/26 | Fri 04/24/26 |  | Azmain Hossain
140 | Manually Scheduled | 2.5.1 | Verify: ≥8-10 demos completed, ≥6 prototypes deployed | Planned | 1 day | Fri 04/24/26 | Fri 04/24/26 |  | Azmain Hossain
141 | Manually Scheduled | 2.5.2 | Verify: SE feedback captured, CRM tagging in use | Planned | 1 day | Fri 04/24/26 | Fri 04/24/26 |  | Azmain Hossain
142 | Manually Scheduled | 2.5.3 | Verify: Factory cost within budget, AI Platform pilot onboarded | Planned | 1 day | Fri 04/24/26 | Fri 04/24/26 |  | Azmain Hossain
143 | Manually Scheduled | 2.5.4 | Phase 1 → Phase 2 gate decision | Planned | 1 day | Fri 04/24/26 | Fri 04/24/26 | 140,141,142 | Richard Dosoo |  | Go/No-Go for SE training expansion.
144 | Auto Scheduled | 3 | PHASE 2: SE TRAINING & EXPANSION | Planned | 20 days | Mon 04/27/26 | Fri 05/22/26 |  |  |  | Weeks 9-12. SEs run demos with AS on standby.
145 | Manually Scheduled | 3.1 | SE Enablement & Training | Planned | 15 days | Mon 04/27/26 | Fri 05/15/26 |  | Martin Davies
146 | Manually Scheduled | 3.1.1 | Create SE enablement pack | Planned | 5 days | Mon 04/27/26 | Fri 05/01/26 |  | Martin Davies | D9
147 | Manually Scheduled | 3.1.2 | Create SE onboarding guide (Cursor + .cursorrules) | Planned | 5 days | Mon 04/27/26 | Fri 05/01/26 |  | Martin Davies | D21
148 | Manually Scheduled | 3.1.3 | Create rapid prototyping playbook | Planned | 5 days | Fri 05/01/26 | Thu 05/07/26 | 146,147 | Martin Davies | D7
149 | Manually Scheduled | 3.1.4 | Conduct SE practice sessions (simulated demos) | Planned | 5 days | Fri 05/01/26 | Thu 05/07/26 | 146 | Martin Davies
150 | Manually Scheduled | 3.1.5 | SE-led demos with AS on standby | Planned | 10 days | Mon 05/04/26 | Fri 05/15/26 | 149 | Martin Davies |  | Transition from AS-led to SE-led.
151 | Manually Scheduled | 3.1.6 | Train SEs on App Factory deployment process | Planned | 5 days | Mon 05/04/26 | Fri 05/08/26 |  | Ben Van Houten |  | SEs deploy to factory independently.
152 | Manually Scheduled | 3.2 | Scenario Expansion & Complex Use Cases | Planned | 10 days | Mon 05/04/26 | Fri 05/15/26 |  | Martin Davies
153 | Manually Scheduled | 3.2.1 | Develop additional scaffold prompts for new prospect scenarios | Planned | 5 days | Mon 05/04/26 | Fri 05/08/26 |  | Martin Davies
154 | Manually Scheduled | 3.2.2 | Test MCP Tier 2 integration for extended demo data | Planned | 5 days | Fri 05/08/26 | Thu 05/14/26 | 153 | Azmain Hossain |  | Outlook, Teams, PowerPoint, Excel MCPs.
155 | Manually Scheduled | 3.2.3 | Test complexity guard across both B5 and AI Platform workflows | Planned | 3 days | Mon 05/11/26 | Wed 05/13/26 |  | Martin Davies |  | SYNC POINT: shared complexity evaluation.
156 | Manually Scheduled | 3.3 | AI Enablement Platform Expansion (Parallel Track) | Planned | 20 days | Mon 04/27/26 | Fri 05/22/26 |  | Azmain Hossain
157 | Manually Scheduled | 3.3.1 | Expand AI Platform to 50-100 users | Planned | 10 days | Mon 04/27/26 | Fri 05/08/26 |  | Azmain Hossain
158 | Manually Scheduled | 3.3.2 | Enable self-service skill creation | Planned | 10 days | Mon 05/04/26 | Fri 05/15/26 |  | Azmain Hossain
159 | Manually Scheduled | 3.3.3 | Build and launch monitoring dashboard (usage, costs, adoption) | Planned | 10 days | Mon 05/04/26 | Fri 05/15/26 |  | Azmain Hossain |  | SYNC POINT: monitoring covers both programmes.
160 | Manually Scheduled | 3.3.4 | Iterate skills based on pilot user feedback | Planned | 15 days | Mon 04/27/26 | Fri 05/15/26 |  | Azmain Hossain
161 | Manually Scheduled | 3.3.5 | Deploy MCP Tier 2 servers | Planned | 10 days | Mon 04/27/26 | Fri 05/08/26 |  | Azmain Hossain
162 | Manually Scheduled | 3.4 | Phase 2 Gate Review | Planned | 1 day | Fri 05/22/26 | Fri 05/22/26 |  | Azmain Hossain | D15
163 | Manually Scheduled | 3.4.1 | Complete Phase 2 handover checklist | Planned | 2 days | Wed 05/20/26 | Thu 05/21/26 |  | Azmain Hossain | D15
164 | Manually Scheduled | 3.4.2 | Verify: SE-led demos completed, deploying independently | Planned | 1 day | Fri 05/22/26 | Fri 05/22/26 |  | Azmain Hossain
165 | Manually Scheduled | 3.4.3 | Verify: Prototype-to-deployment rate ≥60% | Planned | 1 day | Fri 05/22/26 | Fri 05/22/26 |  | Azmain Hossain
166 | Manually Scheduled | 3.4.4 | Verify: AS involvement ≤4 hrs/week | Planned | 1 day | Fri 05/22/26 | Fri 05/22/26 |  | Azmain Hossain
167 | Manually Scheduled | 3.4.5 | Verify: Monitoring dashboard live | Planned | 1 day | Fri 05/22/26 | Fri 05/22/26 |  | Azmain Hossain
168 | Manually Scheduled | 3.4.6 | Phase 2 → Phase 3 gate decision | Planned | 1 day | Fri 05/22/26 | Fri 05/22/26 | 163,164,165,166 | Richard Dosoo
169 | Auto Scheduled | 4 | PHASE 3: SCALE & AUTONOMY | Planned | 20 days | Mon 05/25/26 | Fri 06/19/26 |  |  |  | Weeks 13-16. SEs fully independent. Programme close-out.
170 | Manually Scheduled | 4.1 | SE Full Autonomy & Independent Operations | Planned | 15 days | Mon 05/25/26 | Fri 06/12/26 |  | Martin Davies |  | AS complex/high-stakes only (2-4 hrs/wk).
171 | Manually Scheduled | 4.1.1 | SEs run all demos independently | Planned | 15 days | Mon 05/25/26 | Fri 06/12/26 |  |  |  | Target: 80%+ demos SE-led.
172 | Manually Scheduled | 4.1.2 | AS on-call for complex/high-stakes scenarios only | Planned | 15 days | Mon 05/25/26 | Fri 06/12/26 |  | Martin Davies |  | 2-4 hrs/wk maximum.
173 | Manually Scheduled | 4.1.3 | Develop new demo templates based on field experience | Planned | 10 days | Mon 05/25/26 | Fri 06/05/26 |  | Martin Davies
174 | Manually Scheduled | 4.2 | Solutions Database & App Gallery | Planned | 15 days | Mon 05/25/26 | Fri 06/12/26 |  | Richard Dosoo |  | The compound value play.
175 | Manually Scheduled | 4.2.1 | Design Solutions Database schema | Planned | 5 days | Mon 05/25/26 | Fri 05/29/26 |  | Richard Dosoo |  | Store app specs, components, patterns for reuse.
176 | Manually Scheduled | 4.2.2 | Populate with all deployed app specifications from Phase 1-2 | Planned | 5 days | Fri 05/29/26 | Thu 06/04/26 | 174
177 | Manually Scheduled | 4.2.3 | Build App Gallery browsing interface | Planned | 5 days | Mon 06/01/26 | Fri 06/05/26 |  | Richard Dosoo |  | Browse pre-built features, "shopping cart" experience.
178 | Manually Scheduled | 4.2.4 | Launch App Gallery and community of practice | Planned | 3 days | Fri 06/05/26 | Tue 06/09/26 | 176 | Richard Dosoo
179 | Manually Scheduled | 4.3 | Consulting IP Profiling Strategy Activation | Planned | 15 days | Mon 05/25/26 | Fri 06/12/26 |  | Richard Dosoo |  | Making institutional knowledge AI-accessible.
180 | Manually Scheduled | 4.3.1 | Complete consulting IP profiling workbook | Planned | 5 days | Mon 05/25/26 | Fri 05/29/26 |  | Richard Dosoo | D27
181 | Manually Scheduled | 4.3.2 | Schedule and complete Semarchy MDM integration design meeting | Planned | 3 days | Fri 05/29/26 | Tue 06/02/26 | 179 | Richard Dosoo | D29 | With Jordan Callisher, TSG Product.
182 | Manually Scheduled | 4.3.3 | Configure M365 MCP server for SharePoint document access | Planned | 5 days | Tue 06/02/26 | Sat 06/06/26 | 180 | Azmain Hossain |  | Real-time access to consulting assets.
183 | Manually Scheduled | 4.3.4 | Set up pgvector for semantic search over consulting IP | Planned | 5 days | Tue 06/02/26 | Sat 06/06/26 | 180 | Richard Dosoo |  | RAG for broad questions.
184 | Manually Scheduled | 4.3.5 | Test hybrid MCP + RAG approach end-to-end | Planned | 3 days | Sat 06/06/26 | Wed 06/10/26 | 181,182 | Richard Dosoo
185 | Manually Scheduled | 4.3.6 | Configure Microsoft Purview classification and sensitivity labels | Planned | 5 days | Tue 06/02/26 | Sat 06/06/26
186 | Manually Scheduled | 4.4 | ACE Context Engineering Activation | Planned | 10 days | Mon 06/01/26 | Fri 06/12/26 |  | Azmain Hossain
187 | Manually Scheduled | 4.4.1 | Build ace-context-curator skill specification | Planned | 5 days | Mon 06/01/26 | Fri 06/05/26 |  | Azmain Hossain | D28 | Generate-Reflect-Curate pattern.
188 | Manually Scheduled | 4.4.2 | Implement structured delta bullet storage in SharePoint | Planned | 5 days | Fri 06/05/26 | Thu 06/11/26 | 186 | Azmain Hossain |  | Evolving institutional knowledge capture.
189 | Manually Scheduled | 4.4.3 | Test ACE capturing knowledge from consulting engagements | Planned | 3 days | Tue 06/09/26 | Thu 06/11/26 | 187 | Azmain Hossain
190 | Manually Scheduled | 4.5 | AI Enablement Platform Scale & Maturity (Parallel) | Planned | 20 days | Mon 05/25/26 | Fri 06/19/26 |  | Azmain Hossain
191 | Manually Scheduled | 4.5.1 | Launch cross-team skill sharing | Planned | 5 days | Mon 05/25/26 | Fri 05/29/26 |  | Azmain Hossain
192 | Manually Scheduled | 4.5.2 | Make App Factory Terraform modules available to AI Platform Level 5 deploys | Planned | 5 days | Fri 05/29/26 | Thu 06/04/26 | 190 | Richard Dosoo |  | SYNC POINT: AI Platform users can deploy full web apps.
193 | Manually Scheduled | 4.5.3 | Build automated skill testing pipeline | Planned | 10 days | Mon 06/01/26 | Fri 06/12/26 |  | Azmain Hossain
194 | Manually Scheduled | 4.5.4 | Implement advanced multi-agent workflows (Pipeline, Fan-Out, Review Loop) | Planned | 10 days | Thu 06/04/26 | Wed 06/17/26 |  | Azmain Hossain
195 | Manually Scheduled | 4.5.5 | Consulting IP pipeline feeding both programmes | Planned | 5 days | Tue 06/09/26 | Sat 06/13/26 |  | Richard Dosoo |  | SYNC POINT.
196 | Manually Scheduled | 4.6 | Programme Measurement & Reporting | Planned | 10 days | Mon 06/08/26 | Fri 06/19/26 |  | Azmain Hossain
197 | Manually Scheduled | 4.6.1 | Compile pipeline conversion lift data (tagged vs untagged) | Planned | 5 days | Mon 06/08/26 | Fri 06/12/26 |  |  |  | Target: +5pp win rate.
198 | Manually Scheduled | 4.6.2 | Compile demo velocity data (before vs after) | Planned | 5 days | Mon 06/08/26 | Fri 06/12/26 |  |  |  | Target: 50% reduction.
199 | Manually Scheduled | 4.6.3 | Report prototype-to-deployment rate | Planned | 2 days | Fri 06/12/26 | Mon 06/15/26 | 196,197 | Azmain Hossain |  | Target: ≥80%.
200 | Manually Scheduled | 4.6.4 | Report AI Platform adoption metrics (users, sessions, skills, tokens) | Planned | 2 days | Fri 06/12/26 | Mon 06/15/26 |  | Azmain Hossain
201 | Manually Scheduled | 4.6.5 | Create final programme measurement report | Planned | 3 days | Mon 06/15/26 | Wed 06/17/26 | 198,199 | Azmain Hossain |  | Per D11 spec.
202 | Manually Scheduled | 4.7 | Programme Close-Out & Handover | Planned | 5 days | Mon 06/15/26 | Fri 06/19/26 |  | Azmain Hossain
203 | Manually Scheduled | 4.7.1 | Verify: 80%+ demos SE-led | Planned | 1 day | Mon 06/15/26 | Mon 06/15/26 |  | Azmain Hossain
204 | Manually Scheduled | 4.7.2 | Verify: Prototype-to-deployment ≥80% | Planned | 1 day | Mon 06/15/26 | Mon 06/15/26 |  | Azmain Hossain
205 | Manually Scheduled | 4.7.3 | Verify: AS complex/high-stakes only | Planned | 1 day | Mon 06/15/26 | Mon 06/15/26 |  | Azmain Hossain
206 | Manually Scheduled | 4.7.4 | Verify: App Gallery live | Planned | 1 day | Mon 06/15/26 | Mon 06/15/26 |  | Azmain Hossain
207 | Manually Scheduled | 4.7.5 | Confirm steady-state operations model | Planned | 2 days | Tue 06/16/26 | Wed 06/17/26 | 202,203,204,205 | Richard Dosoo
208 | Manually Scheduled | 4.7.6 | Handover documentation to steady-state team | Planned | 2 days | Wed 06/17/26 | Thu 06/18/26 | 206 | Azmain Hossain
209 | Manually Scheduled | 4.7.7 | Seek budget approval for Martin post-May (beyond 12 weeks) | Planned | 5 days | Tue 06/09/26 | Sat 06/13/26 |  | Richard Dosoo |  | No approval yet for post-May allocation.
210 | Manually Scheduled | 4.7.8 | Programme close-out and lessons learned | Planned | 1 day | Fri 06/19/26 | Fri 06/19/26 | 207 | Azmain Hossain |  | Final programme review.